## Sheet1
ACTION PLAN | MAY | [8 empty] | JUNE | [29 empty] | JULY
| 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
Making Proposal | bar: MAY 23 to MAY 29
Proposal Revision | bar: MAY 30 to JUNE 5
Data Cleaning | bar: JUNE 6 to JUNE 12
Data Processing | bar: JUNE 13 to JUNE 17
Recommendation System | bar: JUNE 18 to JUNE 25
Make Powerpoint | bar: JUNE 26 to JUNE 30
Create Dashboard | bar: JUNE 20 to JULY 3